## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 2 | 4 | 8 | 1 | 0 | 0 | 0 | 0
B | Develop marketing strategy |  | 8 | 12 | 16 | 1 | 0 | 0 | 0 | 0
C | Design brochure | A | 3 | 5 | 8 | 1 | 0 | 0 | 0 | 0
D | Develop product prototype
D1 | Requirements analysis | A | 10 | 15 | 20 | 1 | 1 | 0 | 1 | 1
D2 | Software design | D1 | 15 | 20 | 25 | 0 | 1 | 2 | 0 | 1
D3 | System design | D1 | 16 | 24 | 32 | 1 | 1 | 2 | 0 | 0
D4 | Coding | D2, D3 | 40 | 60 | 80 | 1 | 2 | 2 | 1 | 1
D5 | Write documentation | D4 | 8 | 12 | 16 | 1 | 1 | 1 | 1 | 1
D6 | Unit testing | D4 | 16 | 24 | 32 | 1 | 1 | 1 | 1 | 1
D7 | System testing | D6 | 24 | 36 | 48 | 1 | 1 | 1 | 1 | 1
D8 | Package deliverables | D5, D7 | 4 | 8 | 12 | 1 | 1 | 1 | 1 | 1
E | Survey potential market | B, C | 12 | 18 | 24 | 1 | 0 | 0 | 1 | 0
F | Develop pricing plan | D8, E | 8 | 12 | 16 | 1 | 1 | 1 | 1 | 1
G | Develop implementation plan | A, D8 | 16 | 24 | 32 | 1 | 1 | 1 | 1 | 1
H | Write client proposal | F, G | 8 | 12 | 16 | 1 | 0 | 0 | 0 | 0